## Effort Estimation
Issue # | Summary of tasks | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors
1 | Implement Landing page mockup | 30 | 120 | 60 | Brandon Nguyen | Jermaine Rogelio Bruno, Brandon Nguyen
2 | Implement LostFoundFeed page mockup | 120 | 100 | 60 | Edward Uzueta | Edward Uzueta
7 | Make project page | 30 | 30 | 10 | Edward Uzueta | Edward Uzueta, Michael Lau
10 | Implement LostItemForm page mockup | 120 | 120 | 30 | Michael Lau | Michael Lau, Edward Uzueta
11 | Implement FoundItemForm page mockup | 60 | 30 | 20 | Michael Lau | Michael Lau, Edward Uzueta
12 | Implement admin-login | 120 | 60 | 40 | Brandon Nguyen | Brandon Nguyen
13 | Implement user-login | 30 | 120 | 50 | Brandon Nguyen | Brandon Nguyen
14 | Implement FAQ page mockup | 30 | 30 | 0 | Justin Lai | Justin Lai
15 | Update project page | 30 | 40 | 30 | Brandon Nguyen | Brandon Nguyen
8 | Implement UserDashboard | 180 | 120 | 0 | Brandon Nguyen | Brandon Nguyen
9 | Implement ItemDetailPage | 120 | 180 | 0 | Edward Uzueta | Edward Uzueta, Brandon Nguyen
10 | Implement RecoveryInstructionsPage | 120 | 120 | 0 | Michael Lau | Michael Lau
11 | Implement LocationsDirectoryPage | 180 | 180 | 0 | Michael Lau | Michael Lau
17 | Implement Turn-In InstructionsPage | 120 | 180 | 0 | Michael Lau | Michael Lau
13 | Update Project Page | 60 | 60 | 0 | Brandon Nguyen | Brandon Nguyen
16 | Implement AdminFunctions | 60 | 60 | 0 | Brandon Nguyen | Brandon Nguyen
21 | Implement Playwright tests | 60 | 120 | 0 | Brandon Nguyen | Brandon Nguyen
26 | Implement Notification System | 120 | 120 | 30 | Brandon Nguyen | Brandon Nguyen
29 | Update Project Page | 60 | 60 | 0 | Brandon Nguyen | Brandon Nguyen
30 | Update Playwright tests | 60 | 300 | 90 | Brandon Nguyen | Brandon Nguyen
31 | Update admin functions | 120 | 240 | 60 | Edward Uzueta | Edward Uzueta
32 | Implement admin dashboard | 120 | 240 | 120 | Edward Uzueta | Edward Uzueta
33 | Implement AI-fuzzy search | 180 | 120 | 120 | Michael Lau | Michael Lau
37 | Update submission pages to provide detailed error messages | 120 | 60 | 60 | Brandon Nguyen | Brandon Nguyen
39 | Update submission image rules (fails for larger images) | 120 | 60 | 60 | Brandon Nguyen | Brandon Nguyen
40 | Update Item Feed load times | 60 | 60 |  | Brandon Nguyen | Brandon Nguyen

## Development Experience
Team Member | Software Development Experience (months) | How was coding effort tracked | How was non-coding effort tracked?
Jermaine Rogelio Bruno | 24 | Best guess | Best guess
Michael Lau | 20 | Best guess | Best guess
Brandon Nguyen | 12 | Best guess | Best guess
Edward Uzueta | 36 | Best guess | Best guess
Justin Lai | 26 | Best guess | Best guess